## Guidance
Project Name:
Initial Issue Date:
Date last updated:
Last updated by:
Revision No.
Sections | Guidance | Open
Introduction | A comprehensive risk assessment identifying environment, health and safety impacts and hazards is part of the PBS Environment, Health and Safety Management System . The risk assessment approach should extend beyond prescriptive legislative compliance issues to provide a disciplined process to: | Closed
• Identify the site establish and work related activities that give rise to impacts and hazards at a project;
• Define the potential environmental impacts and health and safety hazards to be risk assessed;
• Analyse the likelihood and consequences to determine a risk ranking;
• Provide treatment of the risk using the “Hierarchy of Control” by eliminating risks so far as reasonably practicable
The evaluation of environmental impacts and health and safety hazards and related risks within the PRR worksheet tab of this workbook provides a standardised and established qualitative approach, which is suitable for typical construction related activities. The principles of AS/NZS ISO 31000:2009 are applied in this process.
Definitions | Aspect - is an organisation‘s activities or services that can interact with the environment. Eg. Excavation
Impact- is any change to the environment, whether adverse or beneficial, wholly or partially resulting from an organisations activities or services. Eg. The impact from excavation could be dust, sediment laden run-off or other impacts.
Activity- The action or process of doing or carrying out work.
Hazard- A source or a situation with a potential for harm in terms of human injury or ill health, damage to property, damage to the environment or a combination of these. i.e. anything that can cause harm to people, plant, equipment and property
Risk -A combination of the likelihood and consequence to a hazard or impact causing injury or harm
Instructions | This template is a controlled document and its structure cannot be altered without the permission of the PBS EHS General Manager
Responsibility | The Project Manager, or nominated representative is responsible for managing this process
Undertaking a Work Health & Safety review (risk assessment) and identification of environmental aspects & impacts: | Work, Health and Safety Legislation requires anyone in control of a workplace to identify work activity hazards and risks with the potential to cause injury or harm to people and to provide control measures to eliminate, so far as reasonably practicable those hazards and risks through control measures consistent with the Hierarchy of Control.
Environmental Protection Legislation includes a general environmental duty that requires a person not to carry out an activity that causes, or is likely to cause, environmental harm unless the person takes all reasonable and practicable measures to prevent or minimise the potential harm
A project Impacts and Hazards Risk Assessment must be undertaken in the planning phase of a project to identify the impacts and hazards of a project with a moderate or greater risk ranking. The project Impacts and Hazards Risk Assessment requires review throughout the life of a project, as construction projects are dynamic in nature. An Impacts and Hazards Risk Assessment may also be required for individual work activities that are complex in nature in addition to the project Impacts and Hazards Risk Assessment.
The identification and assessment of impacts and hazards should consider project specific risks in conjunction with the requirements of the PBS Safety Guide and EHS Alerts to ensure inclusion where required.
Impacts and hazards are assessed using the matrix outlined in the risk ranking tab of this workbook.
The completed Project Risk Register is issued to relevant subcontractors as information to assist in the development of EHS Plans, risk assessments and HR SWMS. Project personnel responsible for reviewing subcontractor EHS documentation shall consider the content of the Project Risk Register when undertaking these reviews.
The table below provides direction on completing the sections of the Project Risk Register (PRR).
PRR Section | Directions
 | The project details and personnel that assisted in the development of the Project Risk Register The team shall also identify applicable PBS EHS Alerts, legislation, codes of practice and/or standards. Where more detailed reference is required this information will be included in the column 'legal and other requirements' related to the key control measure listed.
RISK CONTEXT | Legislation and codes can be found on the SafeWork NSW ACT QLD Websites (Legislation tab) and listed as Appendix 2 of the project EHS&Q Management Plan. The website provides links to codes of practice or other applicable fact sheets, guidelines or industry standards relevant to the development of the PRR
 | The project is broken down into major work activities that follow the sequence of construction. Each individual impact and hazard and related risk identified is evaluated in the PRR Worksheet to determine its risk ranking.
RISK IDENTIFICATION
 | For each potential workplace impact and hazard and related risk identified the Consequence (C) and Likelihood (L) is evaluated to determine a risk ranking using the risk ranking worksheet provided.
RISK RANKING (ANALYSIS)
 | For each potential measure of an impact an identified Risk Ranking (R) will be determined by the Risk Ranking Matrix
RISK EVALUATION
 CONTROL MEASURE (RISK TREATMENT) | Control measures related to each Risk Ranking (R) shall be selected in accordance with the Risk Ranking Summary which provides interpretation of each order of ranking eg: high or critical. When developing control measures the Hierarchy of Control as detailed below must be a primary consideration;
Step 6 - Elimination of risky activities wherever reasonably practicable, if not reasonably practicable minimise risky activities in the following order:
Step 5 - Substitution of risks by providing safer products, materials or processes
Step 4 - Isolation of risks by providing control measures to isolate people from hazards or isolate hazards from people
Step 3 - Engineering out risks by providing mechanical, designed/engineered controls to prevent injury
Step 2 - Administration control of risks by providing procedures such as Lock Out/Tag Out Isolation or Permits To Work
Step 1 - Provide Personal Protective Equipment to reduce the likelihood and severity of injury
A combination of the above measures may be required to minimise the risk to the lowest level reasonably practicable if no single measure is sufficient for that purpose. It should be noted that the best solution possible should be implemented, as the further you move down the options in the Hierarchy of Control the opportunity for human error, mistakes and non compliance will increase.
Where work tasks or activities do not involve high risk construction work, general company safe work practices shall be used. This may include Pre-start/Re-start briefings, site specific hazard awareness/task observations through other documented safe work practices or consultative arrangements or a combination of these. Subcontractors or service providers may choose to manage construction work, which is not high risk with their own general company procedures or processes. It is a requirement that all employees, workers or agents engaged by the subcontractor will have undertaken consultation and training in the content of these company procedures or processes, and that evidence of such training shall be provided to PBS. It is not the practice of PBS to review the content of SWMS or other related procedures for works that are not classified as high risk construction work.
 MONITOR AND REVIEW | The project Project Risk Register requires review throughout the life of a project, as construction projects are dynamic in nature. The review must be conducted in accordance with the frequency outlined in the project EHS&Q Management Plan and may include changes to EHS Plans, SWMS, inductions and training. Where the risk associated with an identified non-conformity is rated as moderate or above a review of the project Risk Register is undertaken at a project level to determine: • the content of the register, i.e. is the hazard and risk, or aspect and impact, related to the non-conformity included in the Assessment; and • the effectiveness of control measures, i.e. short term and long term duration; and • the effectiveness of monitoring activities related to each hazard and risk or aspect and impact.

## PRR
| PBS Project Risk Register | [5 empty] | Acronym | Responsible Positions | Hierarchy of Control |  | Control Selections
[7 empty] | SS | Sub-Contractor Supervisor | 6. Elimination | 0 | %Controls ≥ Engineering | 84.85%
[7 empty] | SM | Site Manager | 5. Substitution | 0 | %Controls < Engineering | 15.15%
[7 empty] | FM | Foreman | 4. Isolation | 24 | ßCheck formulas in L2-L7 if you add rows to ensure range is correct
| Workplace Location: | [5 empty] | CA | Contracts Administrator | 3. Engineering | 60
| Issue Number: | [5 empty] | EHSQ | EHSQ Co-Ordinator | 2. Administration | 15
| Issue Date: | [5 empty] | PE/SE | Project Engineer / Site Engineer | 1.PPE | 2 |  |  | Delete Legislation / Codes not applicable to your jurisdiction
Activity Number | Activity Description | High Risk Construction Work | Responsible Contractor | Hazard / Impact (Worst Credible Consequence) | Likelihood | Consequence | Risk Rating | Critical Control Measures | Hierarchy of Control Highest Level Control? | Monitoring Frequency? | Action by whom (Title) | Status | Legal and other requirements
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | hit by mobile plant (Concrete truck/Pump & Crane) | C Possible | 4 Large | 12 | Lineman to have positive communication with pump operator when positioning the line for the filling of AFS Walls. Pump operator to have direct line of site where concrete boom is to be positioned. Doggman to control the load using a tag line. Clear and precise commands (ie two way radios,hand signals or whistle blasts) to be used when communicating with the operator. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Manual Handling | C Possible | 3 Medium | 9 | Identified control measures must follow the Hierarchy of Control commencing with elimination of the manual handling task where reasonably practicable; followed by the use of mechanical aids to reduce risks related to manual tasks. Ensure you keep the load close to the chest and bend your knees to pick up the load and lift with your legs with your back straight. bend the knees to lower the load then release the load to final position without over extending the back. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2011, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity | Risk of Person Falling more than 2m |  | Falls of persons from Height More than 2m | C Possible | 5 Very Large | 15 | HRSWMS in place for any High Risk Construction works. Keep work areas clean and clear of any excess materials. The Catch or Capture philosophy must be employed as the primary control to prevent the fall or reduce the distance of the fall..Scaffold and /or edge protection to be completed and signed off as ready for use. All loading areas on scaffold to have midrail and top rail installed after load is on scaffold. Mesh infills to be utilised as another option. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity |  |  | Falls of persons from Height Less than 2m | C Possible | 3 Medium | 9 | Identified control measures must follow the Hierarchy of Control commencing with elimination of the task where reasonably practicable. Use of platform ladder or Mobile scaffold as a first action. Use of step ladder for less than 15 min duration or in cases where platform ladder is not viable Handrail installed at opening to prevent person from falling. Scaffold to be completed and signed off as ready for use. All loading areas on scaffold to have midrail and top rail installed after load is on scaffold. Mesh infills to be utilised as another option. Persons are to remain inside the EWP and not stand on the mid rail to over stretch to complete a task. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity |  |  | Cuts and Lacerations | D Unlikely | 3 Medium | 6 | All guards to be fitted to power tools, Leads and tools to be test & tagged by a competent person 3 monthly and any RCD to be test & tagged monthly. Wear the correct PPE for use of power tool and hand tools. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity |  |  | Falls of materials | D Unlikely | 4 Large | 8 | HRSWMS in place for any High Risk Construction works. Correct PPE to be worn when handling materials.VOC for Plant use. Keep EWP clean and clear of any excess materials. The Catch or Capture philosophy must be employed as the primary control to prevent the fall or reduce the distance of the fall. Robust exclusion zones must be on place as a secondary control measure below areas where a risk of fall of materials/tools exists; these exclusion zones must account for potential arc of fall, deflection and bounce. Boom EWPs need to have mesh flooring so the ground is visible below operators feet. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| All Trades / Common Activity |  |  | Dust inhalation | C Possible | 3 Medium | 9 | Correct PPE to be worn, including the use of P2 or higher control masks when working with hazardous materials. Works to be completed in a ventilated area and consider the use of fans if needed. SDS to be communicated to All workers involved in the task via TBT or SWMS. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Welding processes CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| All Trades / Common Activity |  |  | Fatigue | D Unlikely | 2 Small | 4 | Rotate work crews for demanding and heavily physival tasks . Monitor number of workers and hours worked. Contractors to manage own workers in accordance with their own fatigue management process. Min 12hr break between shifts. | 4. Isolation | Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP. Managing the risks of plant in the workplace CoP, Hazardous manual tasks CoP.
| All Trades / Common Activity | Is carried out on or near energised electrical installations or services |  | Electric shock from power tools, leads and equipment | C Possible | 4 Large | 12 | All guards to be fitted to power tools, Leads/tools to be test & tagged 3 monthly by a competent perosn and any RCD to be test & tagged monthly.Register of tagging to be provided to PBS upon completion of tagging. Wear the correct PPE for task or activity undertaken. Leads to be elevated and run through correct cable openings in temp board. No Piggybacking of leads. RCD box to be used to join extension leads if required. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity | Is carried out on or near energised electrical installations or services |  | Electric shock from power tools, leads and equipment - Temp Boards | C Possible | 4 Large | 12 | Temporary boards must be physically secured to prevent overturn of board and front covers must be lockable. Temporary boards must have locked covers over circuit - breakers and RCDs associated with outgoing circuits apart from the main switch/isolating switch which must be readily accessible in the event of an emergency. Permanent House Distribution Boards diplayed power supplier / Authority compliance labels which allow power connection area a higher control level confirming 'test and tag' requirements. Permanent House Distribution Boards must be fitted with machanical protectioin to prevent leads being damaged before use by contractors. RCD Trip times to be recorded monthly | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity | Is carried out on or near energised electrical installations or services Is carried out on or near pressurised gas distribution mains or piping; is carried out on or near chemical, fuel or refrigrant lines; |  | Contact with Live Existing Services | A Almost Certain | 4 Large | 20 | As builts to be received from the client to confirm existing services. Evidence and As Built drawings from client to identify any live and disconnected services within the project boundaries. Service Locator to be engaged to conduct survey of site and provide to PBS. PBS Isolation/Energisation Permit to be used. An Excavation Permit may also be needed. Any live services that remain inside PBS fence line above grade are to be identified using robust barricading and signage. DBYD to be reviewed by PBS and provided to Demolition Contractor. In ground services are to visually marked. | 2. Administration | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity | Is carried out on or near energised electrical installations or services |  | Contact with Overhead Power Lines | B Likely | 4 Large | 16 | No unloading / loading of trucks to happen in the vacinity of these powerlines. All plant to remain at a minimum approach distances to powerlines. Up to 132,000 volts = 3m. 132,000 - 330,000 volts = 6m. Above 330,000 = Tiger Tails to be installed by relevant authority as a visual reminder. Install height/location indicators. Non conductive barrier to be installed between building/plant and power lines. Competent Spotter to have postive communication with plant (UHF radios) and observe plant movements when design envelope has the potential to reach closer than 3 metres to power lines. Install signage as visual reminder. | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity | Risk of Person Falling more than 2m |  | Materials / person falling from a ladder | C Possible | 2 Small | 6 | Platform ladders to be used in the first instance and step ladders can only be used for 15min durations for short spans of works. 3 points of contact at all times. Ladder to be stepped back from any edges of a building at least 3m. Robust exclusion zones must be on place as a secondary control measure below areas where a risk of fall of materials/tools exists; these exclusion zones must account for potential arc of fall, deflection and bounce. | 3. Engineering | Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| All Trades / Common Activity |  |  | Temperature extremes | C Possible | 1 Very Small | 3 | Sunscreen to be worn. Broad brims on hard hats encouraged. Consider rest breaks & job rotation. Undertake work at cooler times of the day. Provide adequate clothing that protects from the elements. | 1. PPE | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity | Risk of Person Falling more than 2m |  | Falls of Person from EWP. | C Possible | 4 Large | 12 | HRSWMS in place , Plant induction tag to be issued before use. Emergency rescue procedures to be developed and signed into by any workers undertaking a task from an EWP. Correct use of EWP's, Exclusion zones to be in place for any working platform 2m or above HIgh risk licence required for the use of booms over the 11m capacity. All works undertaken in accordance with the manufacturers instructions. SWL observed. EWP to be used on level ground. When travelling horizontally the bucket/working platform is to be lowered. All workers to be harnessed to EWP as required by manufacturer. Personnel trained and competent including HRWL for MEWP. Remain clear of edge of structure and adhere to exclusion zones where established and no screening protection provided. No standing on top rails or mid-rails to access work areas, access control bump bar to be fitted to all EWP's as per PBS Alert. Harness to be securely anchored to fixture provided inside EWPHandrail installed at opening to prevent person from falling.. Persons are to remain inside the EWP and not stand on the mid rail to over stretch to complete a task. . | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | fall of Materials & Hand Tools From EWP | C Possible | 3 Medium | 9 | HRSWMS in place for any High Risk Construction works. Correct PPE to be worn when handling materials.VOC for Plant use. Keep EWP clean and clear of any excess materials. The Catch or Capture philosophy must be employed as the primary control to prevent the fall or reduce the distance of the fall. Robust exclusion zones must be on place as a secondary control measure below areas where a risk of fall of materials/tools exists; these exclusion zones must account for potential arc of fall, deflection and bounce. Boom EWPs need to have mesh flooring so the ground is visible below operators feet. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | People and Plant Separation - Excavators | C Possible | 4 Large | 12 | Spotter to have positive communication with excavator operator during the task. Workers to stay outside the swing zone of the excavator. Exclusion zone around the excavation/ excavator to stop any unauthorised entry by other workers on the site. Hand signals or UHF radios to be used as positive communications. Workers to remain out of blind spots of any plant that may be delivering materials to site and spotter to guide any plant to final delivery position. Dogman to remain visible when guiding the delivery or installation of loads and to use positive comms. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Environmental damage from spills and cleaning tools | C Possible | 1 Very Small | 3 | All trowels, tools and equipment to be washed out in a protected and designated wash out area. Concrete pump to blow out in plastic lined bin.Hand tools to be washed out in designated wash out area. All off cuts and construction rubbish to be put into the correct PBS bins only. Ensure that all activities where land is cleared, excavated or disturbed have sediment and erosion control devices implemented and maintained. Provide on-site treatment of any stormwater runoff where required. Determine preventative controls as well as physical controls such as covering of stockpiles or water spraying to eliminate or minimise dust being introduced into the atmosphere. Assess and implement mitigation measures for all noise and vibration related impacts on occupants , visitors, surrounding activities and owners where required to ensure operations do not adversely impact them. Plan and conduct all excavation, movement, treatment, processing or remediation of contaminated soils or groundwater in accordance with the requirements of high risk activities. | 3. Engineering | Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | People and Plant Separation - Mobile plant | C Possible | 4 Large | 12 | Wear seat belt if provided. Driver/operator to be able to see travel path and stop if people walk in direct area. Flashing light to be in prominent position so people will be able to see it and reverse beepers to be in working order. Rear vision mirror to be in working condition | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Sunburn | C Possible | 2 Small | 6 | Short sleeve shirts can be worn onsite. PBS to provide sunscreen stations attached to the nurse calls located onsite. Sunscreen to be worn. Broad brims on hard hats enocuraged. Consider rest breaks & job rotation. Undertake work at cooler times of the day. Provide adequate clothing that protects from the elements. | 1. PPE | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | Plant roll over | D Unlikely | 4 Large | 8 | EWP to be operated on stable ground conditions. Competent VOC'd workers to operate EWP under 11m & Only workers with a High Risk Licence to operate EWP's over 11m. VOC required for mobile plant used on site. Before accessing work areas on the site, operators are to establish a route for safe access and set-up. Considerations of service trenches and penetrations should be taken into account. | 2. Administration | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity | Is carried out on or near energised electrical installations or services Is carried out on or near pressurised gas distribution mains or piping; is carried out on or near chemical, fuel or refrigrant lines; |  | Contact with in-ground services | D Unlikely | 4 Large | 8 | Sucker truck to be used to pot hole every 5m a known services, this will identify the service and the direction that it is going. PBS Excavation permit to be in place before any in-ground works begin. No use of an excavator within 1m of a service unless dispensation has been given by the PBS Regional EHS Manager. HRSWMS to be in place for the task. All inground services are to be located using DBYD, Energise or isolate permit may be necessary depending on the task, HRSWMS needed , identify the risks , hold points, testing procedures and identify Plant needed for reducing the risks etc. | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Excavation work CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | Failure of plant | C Possible | 5 Very Large | 15 | Mobile plant, Excavators and the like, must be correctly maintained and be in good condition for use onsite. All repairs must be attended to before the plant can be used onsite. All lifting gear - Chains and slings must be approved by a competent person. Synthetic slings need to be checked 3 monthly and chains are to be tested yearly, both having a visual inspection before each use. ll lifting equipment must be in good condition and regularley serviced as per manufacturers specs(I.e. Spreader bars, chains, slynthetic slings, clutches). | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Failure of lifting gear | C Possible | 5 Very Large | 15 | All lifting equipment must be in good condition and regularley serviced as per manufacturers specs(I.e. Spreader bars, chains, slynthetic slings, clutches). contractors must not allow any unauthorised entry into exclusion zones. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | Loss of load by the telehandler / Franna | C Possible | 4 Large | 12 | All lifting equipment must be in good condition and regularley serviced as per manufacturers specs(I.e. Spreader bars, chains, slynthetic slings, clutches). Robust fencing shall be installed from a height of 2m-4m (pedestrian fencing type) to not allow any unauthorised entry into exclusion zones. Crane to work lower than 95% capacity. Set up in areas that are approved by the PBS Site Manager. Pre-start to be conducted on Crane before use. Crane to be less than 20yrs old and a 10yr structural inspection completed. When expecting to use crane over 95% capacity a Lift study is to be completed. Do not operate crane in adverse weather conditions which may effect the load or crane. Crane maintenance to be up to date and any repairs to be done prior to lifting. When using excavator as a crane, SWL not be exceeded and All lifting gear to be inspected and approved for use. All loads to be secured when moving around the site via telehander. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections,
| All Trades / Common Activity |  |  | Fire and Explosion when refuelling plant & equipment | C Possible | 3 Medium | 9 | Hot works permit valid for activity if necessary. Area to be clear of any combustable material. Fire fighting equipment to be in date and in the vacinity of the refuelling activity. Haz goods to be stored correctly onsite and in ventilated areas. All personnel using chemicals to be inducted into the SWMS which are to include any controls as per the SDS for the specific product. All Jerry cans used must be returned to the Haz storage and secured, they are not to be left out onsite. Refuelling to be undertaken in identified locations away from other ignition sources. Spill kit relevant to spill risk to be available. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Welding processes CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | Loss of load by the telehandler / Franna | C Possible | 4 Large | 12 | All lifting equipment must be in good condition and regularley serviced as per manufacturers specs(I.e. Spreader bars, chains, slynthetic slings, clutches). Contractors not allow any unauthorised entry into exclusion zones. Crane to work lower than 95% capacity. Set up in areas that are approved by the PBS Site Manager. Pre-start to be conducted on Crane before use. Crane to be less than 20yrs old and a 10yr structural inspection completed. When expecting to use crane over 95% capacity a Lift study is to be completed. Do not operate crane in adverse weather conditions which may effect the load or crane. Crane maintenance to be up to date and any repairs to be done prior to lifting. When using excavator as a crane, SWL not be exceeded and All lifting gear to be inspected and approved for use. All loads to be secured when moving around the site via telehander. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Noise and vibration | C Possible | 2 Small | 6 | When using grinders / tools for an extended period of time, then anti vibration gloves should be worn. Hearing protection should also be worn on top of the site specific PPE requirements. Rotation of workers to be considered for lengthy periods of repetative grinding tasks. | 3. Engineering | Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, Hazardous manual tasks CoP, How to manage work health and safety risks CoP, Managing noise and preventing hearing loss at work CoP, Managing the risks of plant in the workplace CoP, Managing the work environment and facilities CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | roll over of Telehandler | C Possible | 4 Large | 12 | Licenced operator to drive machine only. Telehandler to not be driven within the 'Zone of Influence' of any trenching or excavation works onsite. A designated route for the site to be communicated to all operators which is to be located on the site Notice Board. Operator to achieve confirmation that it is ok to set up outriggers in various locations across the project along the intended fence line location. Telehandler should not be used outside of it Safe working limits as will be identified on the machine & in the operators manual. Lock out tag out procedure to be implemented if machine is faulty until all repairs are made. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | roll over of excavator | D Unlikely | 4 Large | 8 | Excavator is not to be set up inside the "Zone of Influence". ROPS / FOPS to be installed on All plant including but not limited to Grader, Roller, Skid Steer. Do not exceed the SWL of machine. Ensure lifting gear is test and tagged as ready for use by a competent person. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Contact with Hazardous Chemicals or Dangerous Goods | B Likely | 2 Small | 8 | SDS Controls need to be communicated to All workers that are to use and Haz product. The correct PPE is to be worn while completing the task. Chemicals to be correctly labelled and kept in secure storage location on-site. | 2. Administration | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Welding processes CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| All Trades / Common Activity | Risk of Person Falling more than 2m |  | fall of persons in to excavations | D Unlikely | 2 Small | 4 | Flagging installed with signage 2m back from trenching. For Pit excavations over 1.5 - robust fencing to be installed and signage stating "Deep Excavation" and "Authorised persons only". Excavations over 1.5 to be benched, batter or shored. Safe means of access to be provided | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | Loss of load by lifting activities | D Unlikely | 5 Very Large | 10 | All lifting equipment must be in good condition and regularley serviced as per manufacturers specs(I.e. Spreader bars, chains, slynthetic slings, clutches).) Contractors to not allow any unauthorised entry into exclusion zones. Crane to work lower than 95% capacity. Set up in areas that are approved by the PBS Site Manager. Pre-start to be conducted on Crane before use. Crane to be less than 20yrs old and a 10yr structural inspection completed. When expecting to use crane over 95% capacity a Lift study is to be completed. Do not operate crane in adverse weather conditions which may effect the load or crane. Crane maintenance to be up to date and any repairs to be done prior to lifting. When using excavator as a crane, SWL not be exceeded and All lifting gear to be inspected and approved for use. All loads to be secured when moving around the site via telehander. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , . PBSSlinging and Lifting Guidlines
| All Trades / Common Activity | Is carried out on or near energised electrical installations or services Is carried out on or near pressurised gas distribution mains or piping; is carried out on or near chemical, fuel or refrigrant lines; |  | contact with live services in walls / ceilings / Basements | C Possible | 4 Large | 12 | HRSWMS to be in place for the task. Energise or isolate permit may be necessary depending on the task, Aluminium ladders to be used, correct PPE. HOLD POINT - Contractor needs approval to energise, by the PBS Supervisor. Live temporary electrical cabling must be identified with yellow tag tape every 3m,.All temporary electricity provided to socket (general purpose ) outlets must be protected by a Residual Current Device. Isolate live cables where possible, Any works requiring drilling or cutting into areas , materials or structures that MAY contain live electrical shall be thoroughly investigated prior to works. An electrician is required to sign off prior to drilling /cutting within 2m of any alignment of GPO or electrical fitting, light switch. Every cable end (I.e. awaiting termination) must be folded over itself and taped to prevent eye damage and electric shock(in the event of inadvertent energisation). | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity | Involves, or is likely to involve, the disturbance of asbestos Carried out in an area that may have a contaminated atmosphere |  | Unexpected finds | D Unlikely | 4 Large | 8 | PBS site specific Unexpected finds protocol to be followed | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, Excavation work CoP, Hazardous manual tasks CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing electrical risks in the workplace CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity |  |  | Collapse of excavation/trenching | C Possible | 4 Large | 12 | Bench batter or shoring to be installed for any excavations over 1.5m. All machinery not to be located in the 'Zone of Influence' . Any wall that cannot be bench battered or shored is to have a geo-tech certification inspection done before any worker can enter the excavation or trench. Shoring boxes to provide adequate access in/out of the excavation. Adjacent structures, roads and sidewalks must be supported or protected where necessary to prevent collapse. Materials and equipment must be placed at safe distances from the edge of excavations. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | Failiure of concrete pump | D Unlikely | 4 Large | 8 | Operators are to hold relevant HRWL (PB). Before accessing work areas on the site, operators are to establish a route for safe access and set-up. Considerations of service trenches and penetrations should be taken into account. Xrays are to be conducted on a monthly basis and records given to PBS to ensure that pipe thickness does not deteriorate below the minimum density of 2mm of wall thickness in the concrete piping. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | entanglement from the cement mixer | C Possible | 3 Medium | 9 | All guards to be fitted to Mixer engine, Leads to be hung in a position so as not be able to entangle in the movement of the mixer. Mixer to be set up on stable ground. Wear the correct PPE for use of the mixer and don’t have any loose clothing on. RCD Protection from power outlet to be installed and tagged monthly. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP,Managing electrical risks in the workplace CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity | Risk of Person Falling more than 2m |  | Failure of scaffold | C Possible | 3 Medium | 9 | Only competent persons holding the appropriate High Risk Licence suitable to the type of work undertaken must construct, modify or dismantle any scaffold or scafold element.Weekly sign off of access stairing and scaffold decks installed is to be done by the scaffold contractor only. Scaffold system elements must not be constructed of mixed system components unless specifically approved by the manufacturer or a competent person. Scaffolds used for block laying must be fitted with brick guards to protect edges, In Addition, a robust exclusion zone that takes accont for potential arc of fall, deflection and bounce distances and has warning signs displayed must be implemented to prevent access by other workers adjacent to, or behind the block laying activity and the uncured wall. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Fire and explosion when soldering pipes. | C Possible | 3 Medium | 9 | Hot works permit valid for activity. Area to be clear of any combustable material. Fire fighting equipment to be in date and in the vacinity of the refuelling activity. Haz goods to be stored correctly onsite and in ventilated areas. All personnel using chemicals to be inducted into the SWMS which are to include any controls as per the SDS for the specific product. All Jerry cans used must be returned to the Haz storage and secured, they are not to be left out onsite. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Welding processes CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| All Trades / Common Activity |  |  | burns/ flash burn from welding | C Possible | 3 Medium | 9 | Hot works permit valid for activity. Area to be clear of any combustable material. Test n tag of welder. Competent person to use welder. Fire fighting equipment to be in date and in the vacinity of the hot works. Welding Screens required if in trafficable areas. Correct PPE to be worn during the activity. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Welding processes CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| All Trades / Common Activity |  |  | Inhalation of gasses and fumes from welding | C Possible | 3 Medium | 9 | Correct PPE to be worn. Works to be completed in a ventilated area and consider the use of fans if needed. SDS to be communicated to All workers involved in the task via TBT or SWMS. | 2. Administration | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Welding processes CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| All Trades / Common Activity |  |  | Drowning - working near water holes | E Rare | 4 Large | 4 | All water services are to be isolated when excavating. Isolation permit to be completed along with excavation permit. Bungs may need to be placed upstream of workers positions. Life bouys to be placed in the vacinity of nearby ponds. Sed or purpose built dirrectional fencing may need to be installed to direct the flow of potential water accessing the excavation - this may relate to weather events or if draining a line that is upstream of the excavation works. Pumps may need to be installed to remove water Correct PPE needs to be worn I.e. Gum boots in muddy trenches/ excavations. | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Excavation work CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity |  |  | Falls of Persons from Truck | C Possible | 3 Medium | 9 | Mobile handrail system to be in place if person needs to access the trailer. Reo should come pre-slung in secured bundles. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Fire and explosion, Burns - using a grinder to Steel | C Possible | 3 Medium | 9 | Hot works permit valid for activity . Area to be clear of any combustable material. Fire fighting equipment to be in date and in the vacinity of the refuelling activity. Haz goods to be stored correctly onsite and in ventilated areas. Correct PPE must be worn including a face shield and correct gloves. No cotton clothing to be worn during cutting activities as they are highly flammable. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Welding processes CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| All Trades / Common Activity | Risk of Person Falling more than 2m |  | failure of scaffold structure | D Unlikely | 4 Large | 8 | Licenced competent scaffolders to only erect scaffolds and temp stair acesses. .HRSWMS in place for any High Risk Construction works. Correct PPE to be worn when handling materials. The Catch or Capture philosophy must be employed as the primary control to prevent the fall or reduce the distance of the fall. Lanyards/tethers must be used on all tools or equipment. Robust exclusion zones must be on place as a secondary control measure below areas where a risk of fall of materials/tools exists; these exclusion zones must be in place when erecting or dismantling scaffold and must account for potential arc of fall, deflection and bounce. contractors to not allow any unauthorised entry into exclusion zones. | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity | Risk of Person Falling more than 2m |  | Tampering of scaffold structure | E Rare | 4 Large | 4 | Exclusion zone while erecting and dismantling scaffold will be installed. If anyone is caught tampering with scaffold components, then they will be removed from site immediately. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Ingress of water to excavation | E Rare | 4 Large | 4 | All water services are to be isolated when excavating. Isolation permit to be completed along with excavation permit. Bungs may need to be placed upstream of workers positions. Life bouys to be placed in the vacinity of nearby ponds. Sed or purpose built dirrectional fencing may need to be installed to direct the flow of potential water accessing the excavation - this may relate to weather events or if draining a line that is upstream of the excavation works. Pumps may need to be installed to remove water Correct PPE needs to be worn I.e. Gum boots in muddy trenches/ excavations. | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Excavation work CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| All Trades / Common Activity | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | Plant collision from other plant or person | D Unlikely | 4 Large | 8 | Dogman/spotter to control the load using a tag line. Clear and precise commands (ie two way radios,hand signals or whistle blasts) to be used when communicating with the operator. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| All Trades / Common Activity |  |  | Failure of temp props | D Unlikely | 3 Medium | 6 | Inspection on props/timber used Install props as per manufaturers requirements. Correct bolts to be used to secure props. all temporary works must be designed by a qualified, competent and registered engineer In Addition, a robust exclusion zone that takes accont for potential arc of fall, deflection and bounce distances and has warning signs displayed must be implemented to prevent access by other workers adjacent to, or behind the fence installation activity. Fence panels must not be erected in adverse weather conditions. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage and control asbestos in the workplace CoP, How to manage work health and safety risks CoP, How to safely remove asbestos CoP.
| All Trades / Common Activity |  |  | Affects of working in Inclement weather - Cranes & EWP & Concrete Boom | C Possible | 2 Small | 6 | All plant, especially lifting plant are not to work outside the manufacturers reccomendations regards extreme weather I.e. wind speed. If lightning is present in the near sky or immediate sky above then all crane(s), EWP's and concrete booms must be lowered and persons to remain under cover in lunch sheds until the weather passes. In the event that the weather is extreme heat, then workers should consider rotating shifts or start work earlier or out of peak heat periods of the day. Drink plenty of water and take regular rest breaks in shaded or provided lunch sheds that have air-conditioning. In all types of weather you should always wear the appropriate PPE and extras I.e Sunscreen, Rain coat...... | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Reg's 2017, Construction work CoP, Hazardous manual tasks CoP, How to manage work health and safety risks CoP,Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP.
| All Trades / Common Activity |  |  | Environmental Contamination from Spill of Hazardous Chemicals/Substances | E Rare | 3 Medium | 3 | Contractor to provide, and have readily available access to, a spill kit which is appropriately sized for the risk of spill when refuelling or if damage was to occur to a piece of plant and equipment. Workers must be trained in the use of spill kits and the SDS's for chemicals/substances that they are using on this project. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide, Managing risks of hazardous chemicals in the workplace COP
| Asbestos Removal | Involves, or is likely to involve, the disturbance of asbestos Carried out in an area that may have a contaminated atmosphere |  | Exposure to Hazardous Dust | A Almost Certain | 4 Large | 20 | Asbestos Register for relevant building to be requested from Client. Asbestos Removal Control Plan to be in place. Workers and Subcontractor must hold the correct class of licence for the type of asbestos identified to be removed (I.e. over 10m2). Health Monitoring to be done for all workers involved in the task prior to works commencing. Physical barriers to be set up around asbestos removal area with signage. Correct PPE to be worn. Enter Restricted Areas work permit to be issued. HR SWMS to outline methodology for controlling all asbestos dust and loose particles Hold Point - Clearance Certificate to be recieved prior to any other works occuring. Surveillance air monitoring to be done by competent person and results to be entered into monitor register. Asbestos Sub Plan to be developed to outline further controls. Notify Regulator in writing at least 5 days before commencing activity if over the 10m2 or friable. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide, How to safely remove asbestos COP
| Asbestos Removal | Involves, or is likely to involve, the disturbance of asbestos Carried out in an area that may have a contaminated atmosphere |  | PPE, Tools and Waste Contamination | B Likely | 3 Medium | 12 | Waste to be sealed in a container and labelled in accordance with the Globally Harmonised System of Classififcation and labelling to indicate it contains asbestos. Waste must be brought to an Licenced waste disposal facility which accepts asbestos waste. PBS to be given evidence of correct disposal at facility (i.e Tipping Dockets) PPE and Tools must be sealed in containers / double bagged or appropriately decontaminated within the asbestos removal area. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide, Labelling of workplace hazardous chemicals COP, How to safely remove asbestos COP
| Asbestos Removal | Involves, or is likely to involve, the disturbance of asbestos Carried out in an area that may have a contaminated atmosphere |  | Unexpected Find | D Unlikely | 3 Medium | 6 | PBS Unexpected Finds protocol to be followed. Contractor to include unexpected finds protocol in their HR SWMS. Asbestos Register to be updated to include unexpected finding. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Blockwork |  |  | structural wall collapse | C Possible | 5 Very Large | 15 | inspection on props/timber used Install props as per manufaturers requirements. Correct bolts to be used to secure props. Masonary walls must be designed by a qualified, competent and registered engineer . Maximum unsupported wall height is 1.8m. Scaffolds used for block laying must be fitted with brick guards to protect edges, In Addition, a robust exclusion zone that takes accont for potential arc of fall, deflection and bounce distances and has warning signs displayed must be implemented to prevent access by other workers adjacent to, or behind the block laying activity and the uncured wall. Masonary walls must not be erected in adverse weather conditions. Need a documented HOLD POINT to ensure stiffeners and pouring requirements are communicated and undertaken. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| Concrete |  |  | Failure of temporary structure | D Unlikely | 5 Very Large | 10 | Structural engineers certification of the temp deck to be completed and all load point to be in design, this is to be communicated to All workers involved with the deck and all trades supervisors.. Securing requirements, bracing and fixing details must be varified to be in accordance with an approved design and include suitable structural fixings that account for wind load considerations based on locality.HOLD POINT - PBS pre pour inspection check list to be completed before a pour of any decks are to commence. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| Concrete Coring |  |  | Contact with Live Existing Services | B Likely | 4 Large | 16 | Concrete Coring Work Permit to be issued. If services located in direct coring zone then additional Energisation/Isolation Permit to be issued and completed. Visual inspection to be conducted for underslab services. Locator services may be required. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide, Managing electrical risk in the workplace COP
| Concrete Coring |  |  | Hit by Falling Objects | A Almost Certain | 3 Medium | 15 | Concrete Coring Work Permit to be issued.Physical barriers to be in place as an exclusion zone and must take into consideration the arc, fall and bounce of materials and tools underneath the area being cored. Area to be bunted off with signage to prevent unauthorised access. Authorised person only to be in direct workzone. Specific consideration should be made where services or switchrooms are underneath coring location. Coring slurry should be contained for ease of clean up. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide, Managing electrical risk in the workplace COP
| Crane (Franna/Mobile/Crawler/Telehandler) |  |  | Inground services during crane transit onsite | C Possible | 5 Very Large | 15 | TTMP to be established for crane route onsite so it misses any in-ground services trenching. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| Crane (Franna/Mobile/Crawler/Telehandler) | Is carried out in an area at a workplace in which there is any movement of powered mobile plant C10 |  | Plant and People seperation | C Possible | 4 Large | 12 | Contractors to not allow any unauthorised entry into exclusion zones. Crane out riggers to be protected with concrete jersy curbs or simular to prevent contact with trucks and other vehicles. Pedesrian walkways onsite not to be inside or directed to crane work zone(s). Signage in place to communicate that only authorised workers to be in crane work zone. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Crane (Franna/Mobile/Crawler/Telehandler) |  |  | Crane & equipment failure | C Possible | 5 Very Large | 15 | All lifting equipment must be in good condition and regularley serviced as per manufacturers specs(I.e. Spreader bars, chains, slynthetic slings, clutches). Crane to work lower than 95% capacity. Set up in areas that are approved by the PBS Site Manager. Pre-start to be conducted on Crane before use. Crane to be less than 20yrs old and a 10yr structural inspection completed. Lift study for any loads over 20tonne or when expecting to use crane over 95% capacity. Do not operate crane in adverse weather conditions which may effect the load or crane. Crane maintenance to be up to date and any repairs to be done prior to lifting. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Crane (Franna/Mobile/Crawler/Telehandler) | Is carried out in an area at a workplace in which there is any movement of powered mobile plant |  | Crushing a person or property while performing pick and carry tasks with Franna/Telehandler | D Unlikely | 4 Large | 8 | Dogman/spotter to control the load using a tag line. Clear and precise commands (ie two way radios,hand signals or whistle blasts) to be used when communicating with the operator. Stop the Franna/Telehandler movements and use clear communication when dealing with perdestrians and other plant. Operator to obey any and all directions issued by the dogman/spotter. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Crane (Franna/Mobile/Crawler/Telehandler) | Is carried out on or near energised electrical installations or services |  | Contact with Overhead Power Lines | C Possible | 4 Large | 12 | Dogman and Operator to sign into Crane Management Sub Plan. No unloading / loading of trucks to happen in the vacinity of these powerlines. All plant to remain at a minimum approach distances to powerlines. Up to 132,000 volts = 3m. 132,000 - 330,000 volts = 6m. Above 330,000 = 8m.Tiger Tails to be installed by relevant authority as a visual reminder. Install height/location indicators. Non conductive barrier to be installed between plant and power lines. Competent Spotter to have postive communication with plant (UHF radios) and observe plant movements when design envelope has the potential to reach closer than 3 metres to power lines. Install signage as visual reminder. Non conductive tag lines to be used to control load. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide,Managing the risks of plant in the workplace COP, Managing electrical risks in the workplace COP
| Demolition | Demoliton of an element of a structure that is load- bearing or otherwise realed to the physical integrity of the structure |  | Works affect neighbouring structures | C Possible | 3 Medium | 9 | Dilapidation survey to be undertaken by consultant. Prior to works starting, Vibration Monitoring to be in place. Noise monitoring to be in place. Letter box drop to occur in neighbouring properties that might be affected by works. Stakeholder Communication Sub Plan to be in place. Noise Management Sub Plan to be in Place. | 2. Administration | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Demolition | Demoliton of an element of a structure that is load- bearing or otherwise realed to the physical integrity of the structure |  | Uncontrolled Collapse of Structure | C Possible | 3 Medium | 9 | Demolition Plan to be developed outlining sequence of demolition. Where applicable, any structural engineers sign-offs needs to be obtained. Physical Barriers to be in place as an exclusion zone to prevent unauthorised access. "Demolition in progress" signage to be installed. Only licenced contractors to perform works. If structure is over 6m in height then PBS to notify Regulator in writing at least 5 days before commencing works. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide, Demolition Work COP,
| Demolition |  |  | Potential for building to have Hazardous materials | E Rare | 2 Small | 2 | Delapidation survey to be conducted before demolition is to commence. All findings to have controls if Haz materials are to be found inside building. | 2. Administration | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, , Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| Electrical | Is carried out on or near energised electrical installations or services |  | electrocution from commissioning works | C Possible | 4 Large | 12 | HRSWMS to be in place for the task. All inground services are to be located using DBYD, All inground services that are within 1m of the direct work area are to be isolated(as per excavation permit), excavation permit / Energise or isolate permit may be necessary depending on the task, Aluminium ladders to be used, correct PPE. HOLD POINT - Contractor needs approval to energise, by the PBS Site Manager. Live temporary electrical cabling must be identified with yellow tag tape every 3m, where cabling is accessable.Competent Persons must carry out electrical inspection, testing and tagging of RCD's Monthly and leads 3 monthly. All temporary electricity provided to socket (general purpose ) outlets must be protected by a Residual Current Device. Isolate live cables where possible, All contractors shall produce HRSWMS , identify the risks , hold points, testing procedures and identify Plant needed for reducing the risks etc. Drilling & cutting. Any works requiring drilling or cutting into areas , materials or structures that MAY contain live electrical shall be thoroughly investigated prior to works. An electrician is required to sign off prior to drilling /cutting within 2m of any alignment of GPO or electrical fitting, light switch. Electrical apprentices and trades assistants must work under the supervision of a licenced electrician at all times.All electrical work (other than inspection and testing of portable equipment) must be carried out by a licenced electrician & each electrician must varify thier licence before they commence electrical works. Calibration of all testing equipment must be carried out at a minimum yearly. Cordless tools are encouraged to be used before power tools. Every cable end (I.e. awaiting termination) must be folded over itself and taped to prevent eye damage and electric shock(in the event of inadvertent energisation). | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| Electrical | Is carried out on or near energised electrical installations or services |  | electrocution from commissioning works - Temp Boards | B Likely | 5 Very Large | 20 | Install RCD protected temporary boards at each level in nominated location being hard wired with 4mm cable (i.e no spider / wander boards allowed). Temporary boards must be physically secured to prevent overturn of board and front covers must be lockable. Temporary boards must have locked covers over circuit - breakers and RCDs associated with outgoing circuits apart from the main switch/isolating switch which must be readily accessible in the event of an emergency. Temp Boards must have signage installed on the front cover.Lock out/Tag out system to be used when isolation of electrical feed required. Isolation / Energisation Permit to be issued. Live temporary electrical cabling must be identified with yellow tag tape every 3m, where cabling is accessible. Competent Persons must carry out electrical inspection, testing and tagging of leads 3 monthly and a Qualified person must test RCD's monthly. All temporary electricity provided to socket (general purpose ) outlets must be protected by a Residual Current Device. Each Temporary Board & all construction wiring installations must have a completed copy of ACT CES/ NSW CCEW / QLD CTC provided to PBS following each energisation. Electrical apprentices and trade assistants must work under the supervision of a licenced electrician at all times. All electrical work (other than inspection and testing of portable equipment) must be carried out by a licenced electrician & each electrician must verify their licence before they commence electrical works. Calibration of all testing equipment must be carried out as per manufacturers instructions. Cordless tools are encouraged to be used before power tools. Every cable end (I.e. awaiting termination) must be folded over itself and taped to prevent eye damage and electric shock (in the event of inadvertent energisation). RCD Trip Times to be recorded monthly on a register. HR SWMS to include emergency procedure. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| Facade | Risk of Person Falling more than 2m |  | fall of person through facade opening | D Unlikely | 4 Large | 8 | HRSWMS in place for any High Risk Construction works. Correct PPE to be worn when handling materials.VOC for Plant use. Keep EWP clean and clear of any excess materials. The Catch or Capture philosophy must be employed as the primary control so to prevent the fall or reduce the distance of the fall. Lanyards/tethers must be used on all tools or equipment. Robust exclusion zones must be on place as a secondary control measure below areas where a risk of fall of materials/tools exists; these exclusion zones must account for potential arc of fall, deflection and bounce. Robust fencing shall be installed from a height of 2m-4m (pedestrian fencing type). | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Formwork | Risk of Person Falling more than 2m |  | fall of a person from height/ top deck / Penetrations. | E Rare | 4 Large | 4 | HRSWMS in place for any High Risk Construction works. Correct PPE to be worn when handling materials.VOC for Plant use. Keep EWP clean and clear of any excess materials. The Catch or Capture philosophy must be employed as the primary control to prevent the fall or reduce the distance of the fall. Lanyards/tethers must be used on all tools or equipment. Robust exclusion zones must be on place as a secondary control measure below areas where a risk of fall of materials/tools exists; these exclusion zones must account for potential arc of fall, deflection and bounce. Boom EWPs need to have mesh flooring so the ground is visible below operators feet. Robust fencing shall be installed from a height of 2m-4m (pedestrian fencing type). | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| Formwork |  |  | Property damage loading material onto structure | C Possible | 2 Small | 6 | Doggman/spotter to control the load using a tag line. Clear and precise commands (ie two way radios,hand signals or whistle blasts) to be used when communicating with the operator. Stop the Franna/Telehandler movements and use clear communication when dealing with perdestrians and other plant. Operator to obey any and all directions issued by the doggman/spotter. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Formwork |  |  | Failure of temp structure (I.e Point loads on deck, concrete, scaffold access stairs) | D Unlikely | 5 Very Large | 10 | Structural engineers certification of the temp deck to be completed and all load point to be in design, this is to be communicated to All workers involved with the deck and all trades supervisors.. Securing requirements, bracing and fixing details must be varified to be in accordance with an approved design and include suitable structural fixings that account for wind load considerations based on locality.HOLD POINT - PBS pre pour inspection check list to be completed before a pour of any decks are to commence. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| Formwork |  |  | fall of materials / Joists and bearers. | C Possible | 2 Small | 6 | All materials are to be loaded from the bottom. If material is too heavy then team lifting should be done so as to stop any inadvertant drops of timber onto oneself. Only formworkers should be in the direct work area and signage and tape to be erected to communicate to other trades not to enter the work zone. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| Formwork |  |  | Impailement from starter bars | E Rare | 4 Large | 4 | All starter bars are to have plastic caps on them at all times. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| Formwork |  |  | Cuts & skin puntures from nails | B Likely | 2 Small | 8 | When stripping timbers workers must ensure that all timbers are de-nailed, not just knock the nail over but DE-NAIL. All used nails to be placed in PBS bin | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| Hoist | Risk of Person Falling more than 2m |  | Fall of Person | A Almost Certain | 4 Large | 20 | Installation by competent personnel to manufacturer / supplier requirements. Handover certificate to be received from contractor whom erected plant. For erection, dismantle and maintenance - Use of Harness Work Permit to be issued. Harness to be inspected daily before use and maintained as per manufacturer specifications. Person with working at heights ticket to conduct works involving use of harness only. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Hoist |  |  | Plant Failure | C Possible | 4 Large | 12 | Installation by competent personnel to manufacturer / supplier requirements. Handover certificate to be received from contractor whom erected it. Load rating must be clearly identified inside the hoist. Only licensed personnel to operate personnel & materials hoist. Daily operator checks to be completed prior to operating each day. Hoist to be maintained as per manufacturer specs. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Landscaping |  |  | fall of person from moving vehicle - Spray seed truck. | C Possible | 4 Large | 12 | Handrail system to be engineered to restrain the operator whilst on the back of the truck when spraying. Vehicle must not exceed 5km/h during the task and sprayer must come down from the back of the truck after spray task is complete. persons are not to remain up top during normal driving on/off site. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Lift Installation | Risk of Person Falling more than 2m |  | Falls of Persons | A Almost Certain | 4 Large | 20 | Physically fix 50 X 25mm mesh or ply to each lift shaft opening after pouring & prior to lift install commencing. Replace mesh / ply lift door opening protection with dead lock keyed lift cage physically fixed across opening before lift install commencing. Ensure temporary handrail is installed at every level with only working level removed for access but replaced before moving working temp platform. Ensure hand rails balustrades are installed & secured on top of car before works commence. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Mechanical (Air-con) |  |  | Failure of duct hoist | D Unlikely | 3 Medium | 6 | All duct lifters and portable type hoists must have a failsafe system so that in the event of a hoisting wire failure the load cannot fall. In addition, outriggers where fitted must be used, SWL must be clearly marked & only propriety attachments are used and only in accordance with manufacturers instructions. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Mechanical (Air-con) | Is carried out on or near energised electrical installations or services |  | electrocution from commissioning works | C Possible | 4 Large | 12 | HRSWMS to be in place for the task. All inground services are to be located using DBYD, All inground services that are within 1m of the direct work area are to be isolated(as per excavation permit), excavation permit / Energise or isolate permit may be necessary depending on the task, Aluminium ladders to be used, correct PPE. HOLD POINT - Contractor needs approval to energise, by the PBS Site Manager. Live temporary electrical cabling must be identified with yellow tag tape every 3m, where cabling is accessable.Competent Persons must carry out electrical inspection, testing and tagging of RCD's Monthly and leads 3 monthly. All temporary electricity provided to socket (general purpose ) outlets must be protected by a Residual Current Device. Isolate live cables where possible, All contractors shall produce HRSWMS , identify the risks , hold points, testing procedures and identify Plant needed for reducing the risks etc. Drilling & cutting. Any works requiring drilling or cutting into areas , materials or structures that MAY contain live electrical shall be thoroughly investigated prior to works. An electrician is required to sign off prior to drilling /cutting within 2m of any alignment of GPO or electrical fitting, light switch. Electrical apprentices and trades assistants must work under the supervision of a licenced electrician at all times.All electrical work (other than inspection and testing of portable equipment) must be carried out by a licenced electrician & each electrician must varify thier licence before they commence electrical works. Calibration of all testing equipment must be carried out at a minimum yearly. Cordless tools are encouraged to be used before power tools. Every cable end (I.e. awaiting termination) must be folded over itself and taped to prevent eye damage and electric shock(in the event of inadvertent energisation). | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| Piling | Risk of Person Falling more than 2m |  | fall of person into pier holes | D Unlikely | 2 Small | 4 | Pier holes to be protected by a robust and certified handrail system. A certified mesh cover is to also be pinned down over the pier hole inside the fencing. Pier hole methodology to be approved by PBS. | 3. Engineering | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Hazardous manual tasks CoP, Construction work CoP, How to manage work health and safety risks CoP, Work health and safety consultation, coordination and cooperation CoP.
| Piling | Involves, or is likely to involve, the disturbance of asbestos |  | Exposure to Hazardous dust | C Possible | 4 Large | 12 | Test Holes of soil conditions to be completed by consultant and results provided to PBS.Contaminated areas to be bunted off using physical barriers and signage installed. Plastic to be installed over contaminated areas to prevent risk of dust arising until removal process is initiated.Plan created to highlight affected asbestos KNOWN areas, with likely areas also highlighted. This plan is then to be communicated to contractors and used in their internal communications with the workers. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Plumbing |  |  | Ingress of water to excavation | D Unlikely | 4 Large | 8 | All water services are to be isolated when excavating. Isolation permit to be completed along with excavation permit. Bungs may need to be placed upstream of workers positions. Life bouys to be placed in the vacinity of nearby ponds. Sed or purpose built dirrectional fencing may need to be installed to direct the flow of potential water accessing the excavation - this may relate to weather events or if draining a line that is upstream of the excavation works. Pumps may need to be installed to remove water Correct PPE needs to be worn I.e. Gum boots in muddy trenches/ excavations. | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Excavation work CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| Post Tension Stressing |  |  | Equipment Failure | D Unlikely | 4 Large | 8 | Hydraulic Stressing Jack and matching guage calibration certificates to be provided by contractor prior to commencement of any stressing operations. Calibration certificate to be with 12 months and not expired. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide, Managing the risks of plant in the workplace COP
| Post Tension Stressing |  |  | Failure of components or materials | C Possible | 5 Very Large | 15 | Prepour ITP to be completed along with egineers pre pour inspection an provided prior to concrete pour Place solid backing board in position behind stressing conduct prior to installing stressing cables. Ensure barrier installed behind stressing equipment during initial and final stress. ,Signage to be installed whilst stressing.Solid backing board to be installed behind live end when final stressing double live end tendonds Authorised person only to be in direct workzone. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Post Tension Stressing |  |  | Failure of structure or concrete elements. | C Possible | 5 Very Large | 15 | Concrete crush test to be completed and records are within required concrete MPa requirements Place solid back board in position behind stressing conduct prior to installing stressing cables. Ensure barrier installed behind stressing equipment during final stressing procedure. Signage to be installed whilst stressing. Authorised person only to be in direct workzone. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Post Tension Stressing |  |  | Failure of temp structure (I.e Point loads on deck,) | D Unlikely | 5 Very Large | 10 | Engineer to include in drawing or provide written instruction where load points are on deck for bondek or similar, formwork supervisor to provide location sufficient to hold required weight on conventional formwork deck. Flagging or parrawebbing to be installed underneath working deck to prevent workers accessing area under coil of strand. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Reo & Steelfixing |  |  | Failure of temp structure (I.e Point loads on deck,) | D Unlikely | 5 Very Large | 10 | Structural engineers certification of the temp deck to be completed and all load point to be in design, this is to be communicated to All workers involved with the deck and all trades supervisors.. Securing requirements, bracing and fixing details must be varified to be in accordance with an approved design and include suitable structural fixings that account for wind load considerations based on locality.HOLD POINT - PBS pre pour inspection check list to be completed before a pour of any decks are to commence. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide ,
| Roofing / Mesh & Gutters | Risk of Person Falling more than 2m |  | Unsuitable access to roof | D Unlikely | 4 Large | 8 | Stretcher stair to provide access. Scaffold to have weekly certifications completed by competent scaffolder. No one is to alter the scaffold unless they are the employee of the contacted scaffolder. Restricted access to site via locable scaffold tubing entry and roof access register to completed for other trades wanting to enter roof zone. | 4. Isolation | Permits, Pre-starts, TBT's, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Roofing / Mesh & Gutters | Risk of Person Falling more than 2m |  | Falls of Persons | A Almost Certain | 4 Large | 20 | Heavy Duty sarking or safety mesh with adequate overlap and tie points or intermediate battens must be installed. Authorised access to roof only.Safety Mesh to be signed off by competent person and handover to be given to PBS. Voids to be adequately protected prior to accessing roof level (i.e skylights) Where the slope of a roof exceeds 35 degrees the roof is an inappropriate surface to stand on, even with guardrailing or a catch platfrom. In these circumstances, roof workers need a system to prevent both sliding and falling from the perimeter and this must be documented in the HR SWMS. Use of Harness Work Permit to be issued. Harness to be inspected daily before use and maintained as per manufacturer specifications. Person with working at heights ticket to conduct works involving use of harness only. Safety catch netting installed under potential fall zones. Perimeter scaffolding installed around the perimeter. Safety Mesh to be signed off by competent person and handover to be given to PBS. Voids to be adequately protected prior to accessing roof level (i.e skylights) Where the slope of a roof exceeds 35 degrees the roof is an inappropriate surface to stand on, even with guardrailing or a catch platfrom. In these circumstances, roof workers need a system to prevent both sliding and falling from the perimeter and this must be documented in the HR SWMS. Use of Harness Work Permit to be issued. Harness to be inspected daily before use and maintained as per manufacturer specifications. Person with working at heights ticket to conduct works involving use of harness only. Safety catch netting installed under potential fall zones. Perimeter scaffolding installed around the perimeter. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Security (Comms) |  |  | electrocution from commissioning works | C Possible | 4 Large | 12 | HRSWMS to be in place for the task. All inground services are to be located using DBYD, All inground services that are within 1m of the direct work area are to be isolated(as per excavation permit), excavation permit / Energise or isolate permit may be necessary depending on the task, Aluminium ladders to be used, correct PPE. HOLD POINT - Contractor needs approval to energise, by the PBS Site Manager. Live temporary electrical cabling must be identified with yellow tag tape every 3m, where cabling is accessable.Competent Persons must carry out electrical inspection, testing and tagging of RCD's Monthly and leads 3 monthly. All temporary electricity provided to socket (general purpose ) outlets must be protected by a Residual Current Device. Isolate live cables where possible, All contractors shall produce HRSWMS , identify the risks , hold points, testing procedures and identify Plant needed for reducing the risks etc. Drilling & cutting. Any works requiring drilling or cutting into areas , materials or structures that MAY contain live electrical shall be thoroughly investigated prior to works. An electrician is required to sign off prior to drilling /cutting within 2m of any alignment of GPO or electrical fitting, light switch. Electrical apprentices and trades assistants must work under the supervision of a licenced electrician at all times.All electrical work (other than inspection and testing of portable equipment) must be carried out by a licenced electrician & each electrician must varify thier licence before they commence electrical works. Calibration of all testing equipment must be carried out at a minimum yearly. Cordless tools are encouraged to be used before power tools. Every cable end (I.e. awaiting termination) must be folded over itself and taped to prevent eye damage and electric shock(in the event of inadvertent energisation). | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction work CoP, How to manage work health and safety risks CoP, Managing electrical risks in the workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation CoP. PBS Safety Guide .
| Shoring Systems | Risk of Person Falling more than 2m |  | Fall of Person | B Likely | 4 Large | 16 | Visual barrier to be installed minimum of 2m back from edge of excavation or Physical barrier installed if closer than 2m to edge. Suitable access to be provided to excavation that does not expose workers to risk of fall. "Deep Excavation" signage to be installed around edge of excavation where deeper than 1.5m. Only authorised persons to be in area of shoring or deep excavations. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Shoring Systems | Is carried out in or near a shaft or trench with an excavated depth greater than 1.5 metres |  | Collapse of Excavation / Trenching | A Almost Certain | 4 Large | 20 | Excavation Permit required when penetrating the ground 200mm or more. Excavation / Trench must be either benched; battered; shored or a combination of all if deeper than 1.5m; otherwise proceed as per Geotech report requirements. Any amendments outside geotech report must be signed off by relevant qualified engineer prior to works occuring. Physical Barrier to be installed along top of excavation / trench to prevent plant / vehicles entering the zone of influence. Any spoil must not be stored within zone of influence and must be stored on down slope side. A competent person, for example an engineer should design support systems or be involved in selecting other ground collapse control measures, for example trench shields. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Swing Stage Scaffold | Risk of Person Falling more than 2m |  | Fall of Person | A Almost Certain | 4 Large | 20 | Engineers sign off on swing stage drawing/s and engineers design certification letter. Engineer design letter for slab loading where stage inboard counterweighted/anchored. Engineers verfification statement for erection swing stage. Emergency procedure to be documented in HR SWMS for retrieval of injured person. Swing stage work permit to be issued. Locked off/ secure area where swing stage has been set up. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Traffic Control | Is carried out on, in or adjacent to a road that is in use by traffic other than pedestrians; Is carried out in an area at a workplace which therre is any movement of powered mobile plant. |  | Use of plant and equipment on public roads | C Possible | 4 Large | 12 | Spotter to have positive communication with excavator operator during the task. Workers to stay outside the swing zone of the excavator. Exclusion zone around the excavation/ excavator to stop any unauthorised entry by other workers on the site. Hand signals or UHF radios to be used as positive communications. Workers to remain out of blind spots of any plant that may be delivering materials to site and spotter to guide any plant to final delivery position. Dogman to remain visible when guiding the delivery or installation of loads and to use positive comms. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Construction Work CoP, How to manage work health and safety risks CoP, Managing the risk of falls at workplace CoP, Managing the risks of plant in the workplace CoP, Work health and safety consultation, coordination and cooperation, PBS Safety Guide , .
| Traffic Control | Is carried out on, in or adjacent to a road that is in use by traffic other than pedestrians |  | Hit by Moving Vehicular Traffic | A Almost Certain | 4 Large | 20 | Consultant holding correct tickets to provide Traffic Management Plan (including Traffic Control Plan) which is specific to the works on site . Signage and Devices to be set up in accordance with approved Traffic Control Plan by workers who hold the correct tickets. Traffic Controllers to position themselves where an escape route is accessible at all times. Traffic control signs and devices are to be checked daily to confirm they are still erected as per TCP. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Traffic Control | Is carried out on, in or adjacent to a road that is in use by traffic other than pedestrians |  | Impact on current Traffic Conditions | C Possible | 4 Large | 12 | Traffic Management and Traffic Control Plan to be in place which has been selected or created by a competent person. Traffic Control signage and devices to be installed as per approved TCP. No contractor parking on site. Work Zone on the road is only to be utilised for delivery of material and tools. Traffic and Vehicle Management Sub Plan to be in place | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Traffic Control | Is carried out on, in or adjacent to a road that is in use by traffic other than pedestrians; Is carried out in an area at a workplace which therre is any movement of powered mobile plant. |  | Vehicle / Plant Collision | C Possible | 4 Large | 12 | Traffic Management and Traffic Control Plan to be in place which has been selected or created by a person holding the correct tickets if works conducted outside PBS Perimeter Fencing. Traffic Control signage and devices to be installed as per approved TCP. Traffic control signs and devices are to be checked daily to confirm they are still erected as per TCP. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Waterproofing / Epoxy flooring |  |  | Fire or explosion from using bonding/cleaning products | C Possible | 3 Medium | 9 | Fire fighting equipment to be in date and in the vacinity of the hazardous materials thats being used in case of accidental ignition. Haz goods to be stored correctly onsite and in ventilated areas. All personnel using chemicals to be inducted into the SWMS which are to include any controls as per the SDS for the specific product. Contractor to provide Lockable Bunded storage for their Hazardous storage | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS ACT 2011, WHS Reg's 2017, Excavation Work CoP, How to manage work health and safety risks CoP, Construction work CoP, First aid in the workplace CoP, How to manage work health and safety risks CoP, Labelling of workplace hazardous chemicals CoP, Managing risks of hazardous chemicals in the workplace CoP, Managing the risks of plant in the workplace CoP, Preparation of safety data sheets for hazardous chemicals CoP, Welding processes CoP, Work health and safety consultation, coordination and cooperation CoP, PBS Safety Guide .
| Windows | Risk of Person Falling more than 2m |  | Fall of Person | B Likely | 4 Large | 16 | Ticketed Personnel required for operation of EWP. Harness to be worn and connected prior to bucket being raised. Harness to be inspected daily before use and maintained as per manufacturer specificiations. Mobile scaffold to be used. Any mobile scaffold over 4m needs to be erected by a ticketed scaffolder. Loads to arrive pre-slung to eliminate the need for workers to stand on the truck tray. Internal edge protection needed when installing windows from inside the building on any level above ground. | 3. Engineering | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Windows |  |  | Hit by Falling Objects | C Possible | 3 Medium | 9 | Approved, regularly inspected lifting frames to be used. Check suction and battery strength prior to lifting if applicable. Engineered lifting frames to be inspected annually by boiler maker or other competent person to ensure suitability for purpose and be recorded on plant and equipment register. Authorised person only to be in direct workzone. | 4. Isolation | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| Site Specific Controls - Existing residents |  |  | Contact with existing residents or building occupiers | C Possible | 3 Medium | 9 | Interaction with existing residents and occupiers of buildings are to be avoided where possible, contractors are to act in a courteous and considerate manner. Should there be any violence, threats or otherwise from the residents to the contractors PBS are to be advised and due process to take part. | 2. Administration | SWMS Review, Permits, Pre-starts, TBT's, Plans/Drawings, Plant inspections, Onsite inspections, | SM, Foreman, PBSCW, CA, EHS&Q Manager, Contractors Supervisor, HSR, CW's | Open | WHS Act 2011, WHS Regulations 2017, Construction Work COP, How to manage work health and safety risks COP, Work health and safety consultation, coordination and cooperation COP, PBS Safety Guide
| X Neighbouring Businesses | [6 empty] | PBS will either communicate directly (through Letter drops, Public Notice Boards or Consultation sessions) with these entities, or through the client established communication protocols for feedback when assessing HIRAC to be implemented when reducing any potential risk(s) posed.

## Risk Ranking
LIKELIHOOD (L) |  |  | CONSEQUENCE (C) - IMPACT |  |  | RISK RANKING (R) | [5 empty] | RISK SUMMARY
[7 empty] | 1 | 2 | 3 | 4 | 5
A | Almost Certain | Expected (almost certain) outcome in most cases 91 - 100% probable without control measures in place; regular incident trend. | 5 | Very Large | Multiple fatalities due to occupational injury/illness, permanent long term and extensive environmental damage. | A | (A1) 5 | (A2) 10 | (A3) 15 | (A4) 20 | (A5) 21+ | Critical (21+) -These risks are Unacceptable. The work activity or process should be halted until Control Measures are implemented which reduce the risk to significant or less using the Hierarchy of Control. #Detailed research, planning & critical control measures review is required with actions consistent with legal compliance by key stakeholders to eliminate or reduce risk ranking to high or lower consistent with the Hierarchy of Control.
B | Likely | Will probably occur (likely) in most circumstances - 51 - 90% probable without control measures in place; regular incident trend but not almost certain as an outcome or recurrence. | 4 | Large | Fatality due to occupational injury or illness, permanent but localised environmental harm. | B | (B1) 4 | (B2) 8 | (B3) 12 | (B4) 16 | (B5) 20 | High (15-20) - These risks must be reduced wherever possible by implementing higher level Control Measures using the Hierarchy of Control. Detailed review of Critical Control Measures by supervisory staff and workplace managers including consultation with work crew and training in revised system of work. Monitoring of key control measures allocated to specific responsibilities.
C | Possible | May occur some time 31 - 50% probable without control measures in place; infrequent incident trend. | 3 | Medium | Occupational injury or illness that results in permanent disability. Long term damage or pollution or degradation; clean up remediation or rehabilitation will require greater then 1 month. | C | (C1) 3 | (C2) 6 | (C3) 9 | (C4) 12 | (C5) 15 | Moderate (9 -14) Identified Control Measures must be capable of reducing the risk by eliminating or minimising to an acceptable level. Monitoring of key control measures allocated to specific responsibilities.
D | Unlikely | Could occur, but would not be expected - 10 - 30% probable without control measures in place; irregular incident trend on a few occasions. | 2 | Small | Occupational injury or illness that results in off site medical treatment or lost time injury that results in a temporary disability. Short term localised damage or pollution or degradation; clean up remediation or rehabilitation will require up to 1 month. | D | (D1) 2 | (D2) 4 | (D3) 6 | (D4) 8 | (D5) 10 | Low (3-8) -The work is relatively safe and can be managed by routine Control Measures outlined in PBS Safety Guide, routine procedures, guidelines, pre-starts/restarts and Project EHS Rules. No further action is required, unless additional impacts or hazards arise during the work.
E | Rare | Rare (highly unlikely) that this event would occur in the identified circumstances without any control measures in place; < 10% probable. | 1 | Very Small | Occupational injury or Illness that results in on site First Aid treatment. Minor on site environmental damage, pollution or degradation event; clean up remediation or rehabilitation will require less than 24 hours | E | (E1) 1 | (E2) 2 | (E3) 3 | (E4) 4 | (E5) 5 | Negligible (1-2) - No further control measures are required Monitor to ensure risk does not escalate
HIERARCHY OF CONTROL
| 6. Elimination | - Remove hazard or impact completely;
| 5. Substitution | - Replace with a less hazardous;
| 4. Isolation | - Provide controls to isolate people from hazards
| 3. Engineering | - Provide mechanical, designed/engineered controls,
| 2. Administration | - Reduce exposure, procedures, consultation;
| 1. PPE | - To be used in addition to above."

## Attendance Sheet
Workplace PRR Meeting Attendance Register
Date | Title/Role | Name | Signature

## Validation Data
5 Very Large | A Almost Certain | 6. Elimination |  | 1 Very Small | 2 Small | 3 Medium | 4 Large | 5 Very Large
4 Large | B Likely | 5. Substitution | A Almost Certain | 5 | 10 | 15 | 20 | 21+
3 Medium | C Possible | 4. Isolation | B Likely | 4 | 8 | 12 | 16 | 20
2 Small | D Unlikely | 3. Engineering | C Possible | 3 | 6 | 9 | 12 | 15
1 Very Small | E Rare | 2. Administration | D Unlikely | 2 | 4 | 6 | 8 | 10
|  | 1. PPE | E Rare | 1 | 2 | 3 | 4 | 5
Open
Closed