## Slide 1
ESTIMATING and TAKEOFF

## Slide 2: Learning Objectives
Understand the difference in quantity takeoff and estimating
Understand the quantity takeoff process
Identify components used in performing a takeoff
Assign pricing to derived takeoff quantities
Develop an estimate using derived pricing and project commitments
Notes: This PPT presentation helps define the difference between a takeoff and an estimate, and prepares students for the Procore Estimating and Takeoff Module.

## Slide 3: Quantity Takeoff vs. Estimate
A takeoff is determining quantities of Materials and Labor
Estimating is applying costs to the work needed to complete the project

## Slide 4: Quantity Takeoff
An assessment of the quantities of materials and labor to be used in the construction of a project

## Slide 5: Manual Quantity Takeoff
A manual quantity takeoff can include the simple counting of items, or the use of various calculations and formulas to determine the quantity

## Slide 6: The Quantity Takeoff Process
Breaking down a project into manageable units
Determining what quantities are needed
Assessing the material type and quantity detailed on the construction drawings

## Slide 7: Takeoff Components
Each (EA)
Lump Sum (LS)
Linear Foot (LF)
Square Foot (SF)
Cubic Foot (CF)
Cubic Yard (CY)
Board Feet (BF)
Other
Notes: These are the most commonly used components but other are used.

## Slide 8: Work Packages
Material quantities and labor can be combined to create work packages
Individual components taken off in their own units (EA, SF, SY, CF, and CY) and then combined into a work package to tracking of larger scopes

## Slide 9: Labor Production Rates
Known Production Rates are assigned to components of work (and associated quantity) to determine the quantity of hours required to complete a quantity of work

## Slide 10: Using the Procore Takeoff Tool
The Procore Takeoff tool allows for an on-screen (digital) take-off, facilitating, automating, and enhancing accuracy of a takeoff.

## Slide 11: Takeoff Exercises
Takeoff Exercises
    Doors – (Count)
    Flooring – (SF and LF)
    Steel Studs – (LF and SF)
    Footings – (CY & SF)

## Slide 12: Estimating
The process of using the quantities taken off to assess all the costs of a project, including direct costs, indirect costs, overhead costs, and profit.

## Slide 13: Estimating
Assigning Costs
  Labor Costs
  Material/Item Cost
  Equipment Cost
  Other (Subcontractors and Suppliers)

## Slide 14: Assigning Costs to Quantities
Costs can be assigned by:
  Item/Unit Cost
  Work Package Costs

## Slide 15: Using the Procore Estimating Tool
The Procore Estimating tool facilitates, automates, and enhances the accuracy of an estimate.

## Slide 16: Estimating Exercises
Assigning Costs
Item Cost
Labor Costs
Total Costs
Total Labor Hours

## Slide 17: Questions?

## Slide 18
Thank You for Using
PROCORE