## June 24
[PROJECT NAME]
[DATE OF REPORT] | Month-End Financial Review
Project Information |  |  |  |  | Schedule Status Summary |  |  | Notes
Project Name: |  |  |  | INPUT FIELDS | Contract Schedule (Months/Days)
Client: |  |  |  | PX/PM | Contract Start Date
Location: |  |  |  | EXEC | Contract TCO/First Delivery Date
Project Number: |  |  |  |  | Time Extensions Granted
PX: |  |  |  |  | Revised TCO/First Delivery Date | 0
PM: |  |  |  |  | Estimated TCO/First Delivery Date
Contract Summary |  |  |  |  | Days Early/Late (Calendar) | -1
Contract Amount |  |  |  |  | Pending Time Extension (Cal. Days)
Approved Change Orders To Date |  |  |  | 0
Revised Contract Amount
Contract Format (Lump Sum/GMP/Cost-Plus)
General Conditions (Lump Sum/Cost of Work)
Contract Fee Percentage
Change Order Fee Percentage |  |  |  |  | Schedule Exp. w/ Time Extensions | -1
Change Order Summary |  |  |  |  | Billing Summary |  | Y
Changes Approved to Date (PCCO) |  | (% of Orig. Contract) | #DIV/0! | 0 | Current Contract Value |  | N
Approved (Sign not in PCCO) |  |  |  |  | Total Completed and Stored to Date
PCOs Submitted & Pending Approval |  | (% of Current Contract) | #DIV/0! |  | % Complete | #DIV/0!
Change Events/PCOs - Priced Pending Submission |  | (% of Current Contract) | #DIV/0! |  | % Remaining | #DIV/0!
Change Events/PCOs - Not Priced (ROM) |  | (% of Current Contract) | #DIV/0! | 0 | Contract Balance Remaining | 0
Total Pending Changes |  |  | #DIV/0! | 0 | Less: Fee & Markups Remaining
Less: GCs Remaining
Contingency Summary |  |  |  |  | Less: Contingency Balance | 0
Original Contingency |  | (% of Orig. Contract) | #DIV/0! |  | Less: Buyout/Allowances Remaining | 0
Current Contingency |  | (% of Current Contract) | #DIV/0! |  | Plus: Pending Changes | 0
Contingency Usage |  | (% of Orig. Contingency) | #DIV/0! | 0 | Estimated Work to Complete | 0
Contingency Balance (% of Est. Work to Complete) |  |  | #DIV/0! | 0
Financial Risk Summary
Fee Summary
Original Contract Fee ($) |  |  | #DIV/0!
Change Order Fee ($) |  |  | #DIV/0! | 0 | 0 | Current Contract Fee Position
Current Contract Fee
Current Fee - Procore |  |  |  |  | 0 | Fee Writedown Recongnized
Recognized Fee Changes |  |  |  | 0
Div 1 Summary
General Conditions - Budget
General Conditions - Actual CTD | As of: | 2024-07-02
General Conditions - Projection (Current in Procore)
General Conditions - Cost to Complete Projection |  | Procore Up to Date: | 1
General Conditions - Overun/Underun (Current) |  |  |  | 0 | 0 | Threat Adjustment
|  | GC Threat Projection (Not currently Forecasted): |  | 0 | 0 | Subtotal
|  | TOTAL GCs Forecasted with Threats (Overun/Underun): |  | 0
|  | GC Recovery Pending (Owner): |  | 0 | 0 | Owner Recovery Adj.
|  | GC Recovery Projected (Owner): |  | 0
|  | GC Recovery Pending (Subcontractor/Other): |  | 0 | 0 | Sub Recovery Adj.
|  | GC Recovery Projected (Subcontractor/Other): |  | 0 | 0 | Total Recovery
|  | TOTAL GCs Recovery Projection: |  | 0 | 0 | GC Savings/(Under)
|  | TOTAL GCs Forecasted with Recovery (Overun/Underun): |  | 0
Hourly Labor Summary
Labor - Budget (Original from GMP + Executed PCCO's)
Labor - Current Planned | [5 empty] | Track Planned vs actual cost
Labor - Planned Expense to Date | As of: |  |  |  |  | Cost to date vs planed cost
Labor - Actual Cost | As of:
Labor - Overun/Underun (Variance from Plan) |  |  |  | 0 |  | For discussion Below
Labor - Cost to Complete Projection (Unplanned) |  |  |  | 0 | 0 | Additional Threat Adjustment
|  | Labor Threat Projection (Not currently Forecasted): |  | 0 | 0 | Subtotal
|  | TOTAL Labor Forecasted with Threats (Overun/Underun): |  | 0
|  | Labor Recovery Pending (Owner): |  |  |  | Owner Recovery Adj.
|  | Labor Recovery Projected (Owner): |  | 0
|  | Labor Recovery Pending (Subcontractor/Other): |  | 0 | 0 | Sub Recovery Adj.
|  | Labor Recovery Projected (Subcontractor/Other): |  | 0 | 0 | Total Recovery
|  | TOTAL Labor Recovery Projection: |  | 0 | 0 | Labor Savings/Under
|  | TOTAL Labor Forecasted with Recovery (Overun/Underun): |  | 0
Schedule Risk Summary (Est/Broad) |  |  |  |  | 0 | LD Projection (Turn 1 L1-14)
Liqudated Damages Exposure | Daily Rate | Days (Cal.) | 0 | 0 |  | LD Adj. Days
Liqudated Damage Projection |  | Days (Cal.) |  | 0 | 0 | LD Adjustment
Liqudated Damage Recovery (Subs) |  | Days (Cal.) | 0 | 0 | 0 | Total LD
|  | TOTAL KAST LD Projection: | 0 | 0 | 0 | LD Projection (Turn 1 L15-23)
LD Adj. Days
Liqudated Damages Exposure | Daily Rate | Days (Cal.) | 0 | 0 | 0 | LD Adjustment
Liqudated Damage Projection |  | Days (Cal.) |  | 0 | 0 | Total LD
Liqudated Damage Recovery (Subs) |  | TOTAL KAST LD Projection: | 0 | 0
Cost of Work Summary
Contingency Balance (for reference) |  |  |  | 0
[5 empty] | 0 | Should exclude GC's & LDs
THREATS (Impacts or Potential to Impact Fee) Negative Number |  | Threat Estimate (Lump Sum) |  | 0 | 0
0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
0
|  |  |  | 0 | 0
|  |  |  | 0 | 0 | Total Threats
|  | Threat Projection |  | 0
0
RECOVERY (Recovery Plan for Threats) Positive Number |  | Recovery Potential (Lump Sum) |  | 0 | 0
Buyout Savings | [5 empty] | Write Down
Roof Eyebrow Waterprofing Allowance
Roof Material Escalation |  |  |  |  | 0 | Adjust Recovery to match Overage
Roof Vector Mapping Allowance |  |  |  |  | 0 | as there is no shared savings.
Door Protection Allowance |  |  |  |  | 0
OH Door Escalation Allowance |  |  |  |  | 0 | Total Recovery
|  | Recovery Projection |  | 0 | 0 | Subtotal
|  | Subtotal (Threats & Recovery) |  | 0 | 0 | Contingency Offset Adj.
[5 empty] | 0 | Contingency Offset Total
|  | Contingency Offset (If Available) |  | 0 | 0 | Other Offset Adj.
[5 empty] | 0 | Other Offset Total
|  | Other (Offset/Adjustment) |  | 0 | 0 | Total Fee Impact Projection
|  | Fee Impact Projection |  | 0
Miscellaneous Projections
OCIP Savings (Collected) |  |  | #DIV/0! | 0
SDI (Un-Used) |  |  |  |  | 0
Shared Savings (KAST Portion PROJECTED) |  |  | 50% | 0 | 0 | Removed GC savings Acct above
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0 | Total Misc
Misc. Projections |  |  |  | 0 | 0 | Fee Projection
[5 empty] | 0 | Variance (Current Contract Fee)
[5 empty] | 0 | Variance (Original Fee)
[5 empty] | #REF! | 2024-05-01
[5 empty] | #REF! | Variance (June to May)